| Actors | Work | Evidence | Due Date | Discussion: |
| --- | --- | --- | --- | --- |
| Program prioritization working group | Complete rating of program reviews | Report of rating process and summary of rating. | Feb 21st |  |
| Planning Resources Committee (PRC) | Review program prioritization report from working group. | Final report from working group, minutes of PRC. | Feb 23rd |  |
| Cabinet | Input on program prioritization | Committee minutes and recommendation from PRC and Prioritization working group. | Feb. 24th |  |
| Educational Master plan working group | Align and integrate all plans | Prioritization report from PRC, plans and minutes | February 27th |  |
| Educational Master plan working group | Complete the write up of the educational master plan and disseminate internal and external | Educational Master plan | March 20th |  |
| PRC | Review and endorse the educational master plan | Educational master plan | March 22nd |  |
| Cabinet | Review and endorse PRC’s recommendations for the Educational Master Plan | Recommendation from PRC, minutes | March 23rd |  |
| Board | Sharing with the board | Educational Master plan, minutes | March 23rd |  |
| System wide | Develop Work plan based on the Educational master plan with KPI | Educational Master plan | March 23rd |  |
| System wide | Training of Educational Master Plan | Educational Master plan, minutes, wiki page |  | Awareness and training of the document |
| System wide | Implementation of work plans | Educational Master Plan | April 1st |  |